## Programme
No | Description | Key Plant + Labour | Sat |  | Sun |  | Sat |  | Sun |  | Fri |  | Sat |  | Sun |  | Mon |  | Tue |  | Wed |  | Thu |  | Fri |  | Sat |  | Sun
|  | Labour Requirements | 9 | 9 | 9 | 9 | 3 | 3 | 3 | 3 | 0 | 0 | 6 | 6 | 28 | 28 | 28 | 27 | 28 | 28 | 28 | 27 | 27 | 27 | 27 | 27 | 0 | 0 | 0 | 0
| Delivery of Key plant & materials | Pete
1.1 | Plant & Materials | -
1.2 | C40 concrete, pump inlet | - | [15 empty] | 5 |  |  |  | 6 |  |  |  | 6
1.3 | C30 concrete, lock 8 | - | [15 empty] | 1 |  | 6 |  |  |  | 6
| General Labouring | Glen, Colin
2.1 | Pump excavations & lower pound | pump | [10 empty] | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1
2.2 | Install safety fencing + diversions | [11 empty] | 2 |  | 5 | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1
2.3 | Hand mixing | mixer | [11 empty] | 3
2.4 | Prepare for concrete delivery | -
2.5 | Joinery | Gen | [12 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
2.6 | Workboat | Boat | 1 | 1 | 1 | 1 | [6 empty] | 1 |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
| Lock 7 - Pump Inlet Foundations | Matt, Spencer
3.1 | Install cofferdam | 6 tonne Exc, piles |  |  |  |  | 3 | 3 | 3 | 3
3.2 | Excavation to formation level | 6 tonne Exc | [10 empty] | 2
3.3 | Blinding Layer (1.2m3) | mixer | [11 empty] | 3
3.4 | Stage 1 Base Fixing | - | [12 empty] | 5 | 5 | 3
3.5 | Stage 1 Base Formwork | - | [14 empty] | 2
3.6 | Stage 1 Base Concreting (5m3) | poker | [15 empty] | 5
3.7 | Stage 2 Wall Fixing | [17 empty] | 5 | 3 | 3
3.8 | Stage 2 Wall Formwork | acrow | [17 empty] | 2 | 2
3.9 | Stage 2 Wall Concreting (6m3) | poker | [19 empty] | 5
3.1 | Stage 3 Slab Fixing | [21 empty] | 5 | 3 | 3
3.11 | Stage 3 Slab Formwork | acrow | [21 empty] | 2 | 2
3.12 | Stage 3 Slab Concreting (6m3) | poker | [23 empty] | 5
| Lock 9 - 300mm DI Pipeline | Mark, James, Glen
4.1 | Pipelaying in towpath lock 9-8 (400m) | 6 tonne, 5 pipes/day | 4 | 4 | 4 | 4 | [8 empty] | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
4.2 | Sand delivery | Dumper | 1 | 1 | 1 | 1 | [8 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
4.3 | Pipelaying by lock 8 (30m) | 6 tonne, 1 pipes/day
4.4 | Pipelaying in towpath lock 8-7 (300m) | 6 tonne, 5 pipes/day
| Lock 8 - Bywash Repair | Edd, Steve
5.1 | Stage 1 Excavate crown of pipe | mini | [12 empty] | 1 | 1 | 1
5.2 | Stage 1 Hand dig & support | acrow | [13 empty] | 5 | 3 | 3
5.3 | Stage 1 Formwork | poker | [14 empty] | 2 | 2 | 5
5.4 | Stage 1 Concreting (6m3) | poker | [17 empty] | 5
5.5 | Stage 2 Excavate crown of pipe | mini | [16 empty] | 1 | 1 | 1
5.6 | Stage 2 Hand dig & support | acrow | [18 empty] | 3 | 3
5.7 | Stage 2 Formwork | acrow | [18 empty] | 2 | 2 | 5
5.8 | Stage 2 Concreting (6m3) | mixer | [21 empty] | 5
5.9 | Stip formwork | [23 empty] | 2 | 2
5.1 | Backfill | 3 tonne | [22 empty] | 3 | 3
| Towpath Surfacing | Gordon
6.1 | Prepare access above lock 9 | - | 3 | 3 | 3 | 3
6.2 | Excavate kiosk & trenches | 2 tonne | [12 empty] | 4 | 4
6.3 | Fix ducts & formwork | [15 empty] | 4
6.4 | Pour Kiosk Base (1m3) | poker | [15 empty] | 4
6.5 | Towpath Surfacing | Roller | [16 empty] | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
6.6 | Dumper | Dumper | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Training
7.1 | Training | 2 tonne, Dumper, Roller | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1

## Risk assesment
NO | RISK IDENTIFIED | LIKELIHOOD | SEVERITY | TOTAL | PROPOSED MITIGATION
| LIKELIHOOD 1=LOW 2=MED 3=HIGH SEVERITY 1=MINOR 2=A&E 3=FATALITY |  |  |  | TOTAL = LIKELIHOOD x SEVERITY IF TOTAL EQUAL OR GREATER THAN 6 THEN MITIGATION MANDATORY
1 | Public right of way along towpath allows members of public to enter work site at multiple access points. | 3 | 2 | 6 | Erect security fence at each end of worksite, orange fencing at minor points of access. Check to ensure towpath diversion in place with routes clearly signposted.
2 | Boaters operating lock 8 will be within worksite. | 3 | 2 | 6 | Erect orange fence behind mooring bollards along lock 8 to allow continued operation of lock 8 separated from working area.
3 | Risk of drowning from falls into deep water, and empty locks. | 1 | 3 | 3 | Volunteers will be separated from edge of lock 8 by orange fencing, lifering or throw line to be at each worksite, boat personnel only to operate locks. Make a note of non-swimmers.
4 | Boat striking cofferdam below lock 7. | 3 | 1 | 3 | Unlikely to be catastrophic collapse of cofferdam, clay and earth bund to provide extra protection, erect signs warning canal users
5 | Trip, slip or fall from workboat or lock. | 2 | 2 | 4 | Keep boat gunnels, walkways & edges of lock free from obstructions and remove standing water. Walk, don't run. Strim vegetation and backfill obvious potholes.
6 | Trench collapse when working in excavations greater than 1.2m. | 3 | 3 | 9 | Escape ladders to be in place at all times when persons are working in trench. Only a competant person shall determine shoring necessary of trench sides. Use sheet piles & acrow props when excavation exceeds 1.2m or in poor ground conditions.
7 | Water ingress into open excavations. | 2 | 2 | 4 | Monitor canal water levels and control using lock paddles. Provide sump at lowest point of excavation. Use centrifugal pump to remove overnight water, and electric submersible to keep dry.
8 | Excavator striking fibre optic cables in back of towpath. | 3 | 2 | 6 | Use cable tracer to identify position, mark with spraypaint, make excavator operator aware of marks, update marks frequently.
9 | Deliveries damaging utility services across langmans lane bridge. | 3 | 2 | 6 | Obtain record drawings, use cable tracer to identify buried services, obtain emergency contact numbers, use banksman for deliveries.
10 | Entry in/out of busy main road for deliveries and plant movements. | 3 | 3 | 9 | Operatives to wear hi-vis, use banksman at all times, flashing beacons to be fitted to all plant, slew locks to be engaged on swivel tips & excavators when tracking, advance road signs.
11 | Injury from lifting / dropping of heavy items ie: sheet piling, cement, reinforcement bundles. | 3 | 2 | 6 | Operatives to be shown manual lifting practices, heavy items to be lifted by two persons, safety footwear and gloves to be worn, excavator to lift heavy pipe sections and reinforcement bundles.
12 | Re-fuelling splashes / fire. | 1 | 3 | 3 | Plant to be turned off during refueling, allow generators etc to cool down, use funnels and approved containers, store fuel in container, no smoking.
13 | Cement burns to skin, splashes in eye. | 3 | 2 | 6 | Wear eye protection and gloves when handling cementitious materials, avoid dropping concrete from heights, use chutes, wear wellies if standing in concrete, wash off splashes immediately, wear trousers and long sleeves, be aware of sweating, washing facilities & eye wash to be provided in site office
14 | Cuts and eye damage from exposed reinforcement in confined spaces, and fixing steelwork. | 3 | 2 | 6 | Wear eye protection, gloves, trousers and long sleeves. Avoid working too close to others, cover exposed ends of reinforcement with cloth etc
15 | Concrete deliveries falling into excavation when reversing. | 1 | 3 | 3 | Assess route with driver, clear vegetation, provide backstop, use banksman, no-one to remain in excavation when reversing.
16 | Vehicle leaving towpath due to restricted towpath width for deliveries to pipeline, spoil & pipe storage. | 3 | 3 | 9 | Track width of plant minimised, excavated spoil and pipes to be stored in separate barges moored alongside towpath, use banksman when travelling along towpath.
17 | Pipe falls or sways into person during lifting and moving of heavy pipe sections from barge to base of trench. | 2 | 3 | 6 | Use of suitable size excavator, limit outreach of excavator arm, use tested chains and slings, competant person to supervise lifting operations, no person to remain in trench during lifting, operatives to stabilise loose end of pipe using long ropes to maintain distance, experienced plant operators.
18 | Risk of trap injury during fitting of pipe sections. | 3 | 2 | 6 | Only one person allowed in trench to guide pipe into place. They shall act as sole banksman, and not place themselves between pipes at any time excavator is running.
19 | Concrete pipe sections become unstable during excavation of collars. | 3 | 2 | 6 | Maintain pillar of earth beneath centre section of pipe, use wedges to support, use hand tools to avoid placing hands beneath pipe, do not enter trench alongside unstable pipe section.