## Index
Waterway Recovery Group - Risk Asessments
Reference | Description
Annual Works
BW / AW 1 | Vehicle Access to Site | For Information Only
BW / AW 2 | Working Next to the Navigation (1) | For Information Only
BW / AW 3 | Working Next to the Navigation (2) | For Information Only
BW / AW 4 | Operation of Craft | For Information Only
BW / AW 5 | Lifting Operations | For Information Only
BW / AW 6 | Working with Machinery (1) | For Information Only
BW / AW 7 | Working with Machinery (2) | For Information Only
BW / AW 8 | Use of Hand Tools | For Information Only
BW / AW 9 | Use of Ladders | For Information Only
BW / AW 10 | Confined Spaces | For Information Only
BW / AW 11 | Offside Tree & Bush Cutting | For Information Only
BW / AW 12 | Renewing canal coping stones | For Information Only
BW / AW 13 | Grass Cutting ( Small mechanical Cutter ) | For Information Only
BW / AW 14 | Operation of Locks | For Information Only
BW / AW 15 | Driving Bw vehicles ( 1 ) | For Information Only
BW / AW 16 | Driving Bw vehicles ( 2 ) - LORRY | For Information Only
BW / AW 17 | Navigating During Flood Conditions | For Information Only
BW / AW 18
BW / AW 19
BW / AW 20
General Works
BW / GW 01 | Recovery of Debris, Rubbish and Obstructions | For Information Only
BW / GW 02 | Installation and Replacement of Corporate Signage | For Information Only
BW / GW 03 | Maintenance to Long Term / Visitor Moorings | For Information Only
BW / GW 04 | Electrical / Mechanical Works | For Information Only
BW / GW 05 | Routine Lock Maintenance (1) | For Information Only
BW / GW 06 | Routine Lock Maintenance (2) | For Information Only
BW / GW 07 | Sanitary Station Cleaning | For Information Only
BW / GW 08 | Working with Pressure Washers | For Information Only
BW / GW 09 | General Painting Works | For Information Only
BW / GW 10 | Excavation and Filling Operations | For Information Only
BW / GW 11 | Installation of Fencing / Bollards | For Information Only
BW / GW 12 | Piling Works | For Information Only
BW / GW 13 | Feeder Maintenance | For Information Only
BW / GW 14 | Water Control / Operation of Back Pumps | For Information Only
BW / GW 15 | Cleaning Weirs & Culverts | For Information Only
BW / GW 16 | Dredging Works | For Information Only
BW / GW 17 | Working on Canal / River weirs | For Information Only
BW / GW 18 | Putting on of Flood gates at locations on the GUCN | For Information Only
BW / GW 19
BW / GW 20
WRG Restoration Projects
WRG/LANC 01 | Removal of silt and debris by hand from the Lock Chambers at Tewitfied | For Information Only
WRG/LANC 02 | Use of Hand Tools
WRG/LANC 03 | Use of Ladders | For Information Only
WRG/LANC 04 | Confined Spaces
WRG/LANC 05 | Sharp Drops
WRG/LANC 06 | Use / Spraying of Herbicidal Weed Killers | For Information Only
WRG/LANC 07 | Removal of silt and debris from derelict By-wash
WRG/LANC 08 | Operation of Plant and Vehicles On or close to site
WRG/LANC 09 | Working with machinery / plant on site (including cement mixers, brush cutters and low power generators)
WRG/LANC 10 | Mixing and using Mortar and Cement
WRG/LANC 11 | Manual Handling
WRG/LANC 12 | Working adjacent to a watercourse and farm land (illness)
WRG/LANC 13
WRG/LANC 14
WRG/LANC 15

## Blank
Region |  | Canal / Waterway
Sawley Marina |  | Grantham Canal
Planned Operation
Planned Task / Activity
Exposed Groups / Individual
Hazardous Event & Potential Causes |  |  | Likelihood | Severity | Risk
Control Measures |  |  |  |  | Action
Future Measures to be Considered For Evaluation (to be completed during or after the task / activity)
Conclusion - Task Ok to Proceed
Reference No | Assessment Date | Issue No. |  | Review Date
Assessed By: |  | Authorised By:

## BW - AW 01
Region |  | Canal / Waterway
Sawley Marina |  | Grand Union Canal ( North )
Planned Operation
General Works Programme
Planned Task / Activity
Vehicular Access to Site
Exposed Groups / Individual
BW Staff / General Public
Hazardous Event & Potential Causes |  |  | Likelihood | Severity | Risk
1. Collision with other vehicles / pedestrians / structures due to loss of vehicle control, incompetence, access to site via narrow roads with poor visibility, poor weather conditions. |  |  | Unlikely | Lost time to Fatality | High
2. Vehicles reversing causing collision with other vehicles, pedestrians or structures |  |  | Unlikely | Lost time to Fatality | High
3. Unsafe vehicle due to poor maintenance causing the above |  |  | Unlikely | As Above | High
Control Measures |  |  |  |  | Action
1. Staff awareness of risks. All BW staff have experience of the routes used to the sites. Journey planning for all routes. Use of hands free phones. Staff to assess specific risks before work commences. Consider the need to sign the site entrance, limit speed once off public roads to 5 m.p.h. Consider need for a banksman to lead in delivery vehicles etc. If access is from an embanked area, Bank to be assessed for stability by a competant engineer. Consider need for fencing for demarkation of bank edge. |  |  |  |  | Staff
2. As above. When appropriate, banksman to assist with reversing. Audible warning on some vehicles. |  |  |  |  | Staff
3. Staff carry out daily vehicle checks. Regular vehicle servicing. Legal requirements (MOT etc.) |  |  |  |  | Staff
Future Measures to be Considered For Evaluation (to be completed during or after the task / activity)
Advance driving training currently being considered by BW on a national basis
Conclusion - Task Ok to Proceed
Task ok to proceed
Reference No | Assessment Date | Issue No. |  | Review Date
BW / AW 01 | 2001-09-04 | 1 |  | Ongoing
Assessed By: |  | Authorised By:
Darren Bramhall

## BW - AW 02
Region |  | Canal / Waterway
Sawley Marina |  | Grand Union Canal ( North )
Planned Operation
General Works Programme
Planned Task / Activity
Working adjacent to the Navigation (1)
Exposed Groups / Individual
BW Staff
Hazardous Event & Potential Causes |  |  | Likelihood | Severity | Risk
1. Falling / loss of mobility through slips, trips or falls causing minor / major injuries. |  |  | Likely | First Aid / Major Injury | High
2. Assault from general public |  |  | Ext.Unlikely | Lost time | Low
3. Livestock / animal attack |  |  | Unlikely | First Aid | Low
Control Measures |  |  |  |  | Action
1. Considered high risk due to number of incidents. Use of Safety Footwear at all times. Staff to report in at end of shifts. Manditory inspection procedures identify repairs and minor works required to rectify defects. Staff to carry out any works required to provide safe access / egress for work area and for pedestrians. Consider need for site fencing and signage. |  |  |  |  | WS / Staff
2. Risk considered acceptable. First Aid kits available in vehicles, lock sites and work boats Staff to report in at end of shift. Staff to follow BW 'Working Alone' Safety Guidence S10.3.3 |  |  |  |  | Staff
3. Risk considered acceptable. First Aid kits available in vehicles, lock sites and work boats. Staff to report in at end of shift. |  |  |  |  | Staff
Future Measures to be Considered For Evaluation (to be completed during or after the task / activity)
Conclusion - Task Ok to Proceed
Risks considered acceptable. Task ok to proceed.
Reference No | Assessment Date | Issue No. |  | Review Date
BW / AW 02 | 2001-09-04 | 1 |  | Ongoing
Assessed By: |  | Authorised By:
Darren Bramhall

## BW - AW 03
Region |  | Canal / Waterway
Sawley Marina |  | Grand Union Canal ( North )
Planned Operation
General Works Programme
Planned Task / Activity
Working Next to Navigation (2)
Exposed Groups / Individual
BW Staff
Hazardous Event & Potential Causes |  |  | Likelihood | Severity | Risk
1. Contact with water causing a micro biological hazard. Illnesses including Leptospirosis. |  |  | Ext. Unlikely | Lost Time to Fatality | Low
2. Immersion in water causing hypothermia / drowning due to slips, trips or falls |  |  | Unlikely | Fatality | High
3. Contact with underwater hazards causing minor / major injuries |  |  | Unlikely | Major Injury | Medium
Control Measures |  |  |  |  | Action
1. Risk considered low. Preventative and protective measures used such as Leptospirosis cards, barrier creams, good hygiene and personal protective clothing to minimise risk |  |  |  |  | WS Staff
2. Staff awareness reduces risk. Rescue lines and Thermal blankets available on work boats Follow same control measures as G2 - 1 (Slips, Trips or Falls) |  |  |  |  | WS Staff
3. First Aid policy, Needles / Syringes policy applicable to reduce risk. Staff Awareness and provision of Personal Protective Equipment. All vehicles, lock sites and boats have first aid kits |  |  |  |  | WS Staff
Future Measures to be Considered For Evaluation (to be completed during or after the task / activity)
Conclusion - Task Ok to Proceed
Once preventative and protective measures in place risk considered acceptable. Task ok to proceed.
Reference No | Assessment Date | Issue No. |  | Review Date
BW / AW 03 | 2001-04-03 | 1 |  | Ongoing
Assessed By: |  | Authorised By:
Darren Bramhall

## BW - AW 04
Region |  | Canal / Waterway
Sawley Marina |  | Grand Union Canal ( North )
Planned Operation
General Works Programme
Planned Task / Activity
Operation of Water born Craft
Exposed Groups / Individual
BW Staff / Navigation Users
Hazardous Event & Potential Causes |  |  | Likelihood | Severity | Risk
1. Loss of boat control and crushing between boats and solid |  |  | Unlikely | Major Injury/ | Medium
objects caused by operator error. |  |  |  | Fatality
2. Access and egress on/off craft and movement on craft causing |  |  | Unlikely | Lost Time | Medium
slips, trips and falls due to poor housekeeping, slippery surfaces
3. Release of energy from burst hydraulic and water pressure hoses |  |  | Unlikely | Major Injury | Medium
Control Measures |  |  |  |  | Action
1. Only experienced and trained operators used for control of craft. |  |  |  |  | Staff
2. Provision of appropriate safety clothing and footwear. Buoyancy aids, Throw Lines |  |  |  |  | WS
and Thermal Blankets available on the craft. All craft have non-slip decking and |  |  |  |  | Staff
gunnells. Supervision of housekeeping.
3. All machines comply with EC directive on location and protection of hydraulic pipes, |  |  |  |  | WS
particularly those installed at operating position. Regular inspections and maintenance |  |  |  |  | Staff
of craft.
Future Measures to be Considered For Evaluation (to be completed during or after the task / activity)
Conclusion - Task Ok to Proceed
Risk acceptable - Task ok to proceed.
Reference No | Assessment Date | Issue No. |  | Review Date
GWP/CC/G4 | 2001-09-04 | 1 |  | Ongoing
Assessed By: |  | Authorised By:
Darren Bramhall

## BW - AW 05
Region |  | Canal / Waterway
Sawley Marina |  | Grand Union Canal ( North )
Planned Operation
General Works Programme
Planned Task / Activity
Lifting Operations (manual / mechanical)
Exposed Groups / Individual
BW Staff / General Public
Hazardous Event & Potential Causes |  |  | Likelihood | Severity | Risk
1. Poor Manual handling caused by lifting and handling of materials |  |  | Unlikely | Three Day | Medium
or loads |  |  |  | Accident
2. Contact with overhead cables or structures causing damage or |  |  | Unlikely | Fatality | High
Electrocution
3. Mechanical lifting with Hiab or Crane Boat causing loss of load |  |  | Unlikely | Major Injury | Medium
control due to incorrect use of equipment, inadequate maintenance
Control Measures |  |  |  |  | Action
1. Staff awareness and Video training. Individual assessment of manual handling |  |  |  |  | Staff
in accordance with BW Safety procedures. Limit manual handling to 25kg
where possible.
2. Staff vigilance for presence of overhead cables or structures. Staff to assess each site |  |  |  |  | Staff
and a banksman will assist with all lifting operations. If services present implement control
measures outlined in BW guidence 'Avoiding Danger from Underground / Overhead
Services'.
3. Only trained and competent staff used for this operation. Regular recorded inspections |  |  |  |  | WS
are carried out on all lifting gear and machinery. Banksman to assist with lifting operation |  |  |  |  | Staff
and to keep the general public away from the slewing area. Staff to carry out a visual
inspection of lifting equipment before use. Refer to BW safety policy for lifting operations
Appointed person to carry out all lift planning as per LOLER 1998 regs, BS 7121 part 1
BS 7121 part 3
Future Measures to be Considered For Evaluation (to be completed during or after the task / activity)
Conclusion - Task Ok to Proceed
Risk considered acceptable if BW Guidance is adhered to. Task ok to proceed
Reference No | Assessment Date | Issue No. |  | Review Date
GWP/CC/G5 | 2001-09-04 | 1 |  | Ongoing
Assessed By: |  | Authorised By:
Darren Bramhall

## BW - AW 06
Region |  | Canal / Waterway
Sawley Marina |  | Grand Union Canal ( North )
Planned Operation
General Works Programme
Planned Task / Activity
Working with Machinery (Including Chainsaws) (1)
Exposed Groups / Individual
BW Staff
Hazardous Event & Potential Causes |  |  | Likelihood | Severity | Risk
1. Exposure to fumes, vapours including exhaust fumes causing asphyxiation, respiratory disease, eye injuries or fire / explosion. |  |  | Likely | Major Injury | High
2. Exposure to chemical hazards causing the above conditions |  |  | Unlikely | Major Injury | Medium
3. Exposure to excessive noise >85dba causing hearing impairment. |  |  | Unlikely | Major Injury | Medium
4. Exposure to Vibration causing HAVS or muscular skeletal injuries |  |  | Unlikely | 3 Day | Medium
Accident
Control Measures |  |  |  |  | Action
1. Follow COSHH Assessments. Regular servicing of all plant used for the operation. |  |  |  |  | WS
Consider the positioning of the process for ventalation requirements. Use identified Personal |  |  |  |  | Staff
Protective Equipment at all times whilst using or in the vicinity of working machinery.
2. Follow COSHH Assessments. Supervisor to request specific COSHH Assessments for |  |  |  |  | WS
any materials not already covered in the Health & Safety Plan. Staff awareness. |  |  |  |  | Staff
3. Wear Ear Defenders. Reduce exposure time to a minimum |  |  |  |  | WS
Staff
4. Monitor exposure time to vibration level as per HSE's guidance. Use appropriate PPE. |  |  |  |  | WS
Waterway Supervisors to obtain vibration level information from plant hire companies or |  |  |  |  | Staff
suppliers. Regular maintenance of all plant and machinery.
Future Measures to be Considered For Evaluation (to be completed during or after the task / activity)
Conclusion - Task Ok to Proceed
Risks considered acceptable once preventative and protective measures in place. Task ok to proceed.
Reference No | Assessment Date | Issue No. |  | Review Date
GWP/CC/G6 | 2001-09-04 | 1 |  | Ongoing
Assessed By: |  | Authorised By:
Darren Bramhall

## BW - AW 07
Region |  | Canal / Waterway
Sawley Marina |  | Grand Union Canal ( North )
Planned Operation
General Works Programme
Planned Task / Activity
Working with machinery (Including Chainsaws) (2)
Exposed Groups / Individual
BW Staff
Hazardous Event & Potential Causes |  |  | Likelihood | Severity | Risk
1. Contact with moving parts caused by operator error / unguarded machinery or slips, trips or falls. |  |  | Unlikely | Major Injury | Medium
machinery or slips, trips or falls.
2. Ejection of Material caused by unguarded machinery |  |  | Unlikely | Lost Time | Medium
3. Poor Manual handling caused by lifting and handling of machinery |  |  | Unlikely | Three Day | Medium
Accident
4. Electrocution due to poor equipment maintenance, Incorrect power supply, water ingress and operator error
supply, water ingress and operator error |  |  | Unlikely | Fatal | High
Control Measures |  |  |  |  | Action
1. Trained and experienced operator only used for operation. Appropriate guards provided |  |  |  |  | WS
and adherence to manufacturers manual. Use of appropriate PPE. Follow control |  |  |  |  | Staff
measures for trips, slips or falls G2-1. Regular maintenance of plant and machinery.
2. Control measures as above. |  |  |  |  | WS
Staff
3. Staff awareness and Video training. Individual assessment of manual handling
in accordance with BW Safety procedures. Limit manual handling to 25kg |  |  |  |  | WS
where possible. |  |  |  |  | Staff
4. Only trained staff operate machinery. Use of appropriate PPE. Regular inspections and |  |  |  |  | WS
maintenance of machinery. |  |  |  |  | Staff
Future Measures to be Considered For Evaluation (to be completed during or after the task / activity)
Conclusion - Task Ok to Proceed
Risk considered acceptable once preventative and protective measures in place.
Reference No | Assessment Date | Issue No. |  | Review Date
GWP/CC/G7 | 2001-09-04 | 1 |  | Ongoing
Assessed By: |  | Authorised By:
Darren Bramhall

## BW - AW 08
Region |  | Canal / Waterway
Sawley Marina |  | Grand Union Canal ( North )
Planned Operation
General Works Programme
Planned Task / Activity
Use of Hand Tools
Exposed Groups / Individual
BW Staff
Hazardous Event & Potential Causes |  |  | Likelihood | Severity | Risk
1. Use of non-powered hand tools causing striking, cutting, |  |  | Unlikely | First Aid to | Medium
ejection of material, dust inhalation, crushing and trapping |  |  |  | Major Injury
due to poor equipment maintenance, operator error or poor
housekeeping
Control Measures |  |  |  |  | Action
1. Provision of Personal Protective Equipment suitable for specified task. Trained and |  |  |  |  | WS
experienced operators used. Good equipment selection, inspection and maintenance. |  |  |  |  | Staff
Appropriate guards supplied. Supervision of housekeeping and ensure proper storage of
tools. Carry out COSHH assessment where appropriate.
Future Measures to be Considered For Evaluation (to be completed during or after the task / activity)
Conclusion - Task Ok to Proceed
Risk considered acceptable - task ok to proceed.
Reference No | Assessment Date | Issue No. |  | Review Date
GWP/CC/G8 | 2001-09-04 | 1 |  | Ongoing
Assessed By: |  | Authorised By:
Darren Bramhall

## BW - AW 09
Region |  | Canal / Waterway
Sawley Marina |  | Grand Union Canal ( North )
Planned Operation
General Works Programme
Planned Task / Activity
Access using Ladders / Access onto Craft
Exposed Groups / Individual
BW Staff
Hazardous Event & Potential Causes |  |  | Likelihood | Severity | Risk
1 Use of ladders for access to work area causing exposure to |  |  | Unlikely | Major Injury | High
potential falls from heights and falling objects. Causes include |  |  |  | to Fatality
working at heights, unsecured ladders, overbalancing, over reaching
,uneven surface at foot of ladder, slipping on rung or a defective
ladder.
2. Accessing moored craft causing exposure to slips, trips or falls. |  |  | Unlikely | Major Injury | High
Control Measures |  |  |  |  | Action
1. All ladders to meet BS EN 131. All metal ladders will have slip resistent rubber or plastic |  |  |  |  | WS
feet. All ladders will be regularly inspected. Ladders to be tied securely and footed on |  |  |  |  | Staff
a level surface. All ladders to be the correct length and set at the correct angle.
No ladder to be used in excess of 11m long and should extend at least 1.05m above the
landing place. Only commercial grade ladders used ie. Grade 2 or 3.
2. Ladders located at mooring sites for access onto craft are inspected on a monthly basis |  |  |  |  | WS
and any defects are reported to the Waterways Supevisor. Where ladders are not available |  |  |  |  | Staff
use Youngman stagings to access craft.
Future Measures to be Considered For Evaluation (to be completed during or after the task / activity)
Conclusion - Task Ok to Proceed
Risk considered acceptable - task ok to proceed.
Reference No | Assessment Date | Issue No. |  | Review Date
GWP/CC/G9 | 2001-09-04 | 1 |  | Ongoing
Assessed By: |  | Authorised By:
Darren Bramhall

## BW - AW 10
Region |  | Canal / Waterway
Sawley Marina |  | Grand Union Canal ( North )
Planned Operation
General Works Programme
Planned Task / Activity
Confined Spaces
Exposed Groups / Individual
BW Staff
Hazardous Event & Potential Causes |  |  | Likelihood | Severity | Risk
1. Entry into a confined space with potential exposure to Gases, |  |  | Unlikely | Fatality | High
Fumes or vapours, Oxygen deficiency and entrapment or
disabling injury.
Control Measures |  |  |  |  | Action
1. Follow BW Safety Procedures for Confined Spaces. A fully trained, competant person to |  |  |  |  | WS
assess the Hazard Level before entry into a confined space as per BW policy. |  |  |  |  | Staff
If the Hazard Level is 1 or 2 then only trained confined spaces staff will undertake the |  |  |  |  | WS
task if it is necessary. Staff awareness and training on confined spaces and BW Safety |  |  |  |  | Staff
Policy.
Future Measures to be Considered For Evaluation (to be completed during or after the task / activity)
Conclusion - Task Ok to Proceed
Task ok to proceed if BW Safety Policy on Confined Spaces is adhered to.
Reference No | Assessment Date | Issue No. |  | Review Date
GWP/CC/G10 | 2001-09-04 | 1 |  | Ongoing
Assessed By: |  | Authorised By:
Darren Bramhall

## BW - AW 11
Region |  | Canal / Waterway
Sawley Marina |  | Grand Union Canal ( North )
Planned Operation
General Works Programme
Planned Task / Activity
Offside Tree & Bush Cutting
Exposed Groups / Individual
BW Staff
Hazardous Event & Potential Causes |  |  | Likelihood | Severity | Risk
1.Machine maintenance, Injury from the moving parts of the machinary |  |  | Likely | Major Injury | Medium
Fatality
2. Access along the towpath , Falling in to the navigation |  |  | Likely | Major Injury | High
3.Accessing on and of the work boats, Slips / trips and falls, |  |  | Likely | Minor Injury | Low
Control Measures |  |  |  |  | Action
1. Engines to be switched off and guards to be in place and adhere to manufactorers manuel |  |  |  |  | Staff
PPE to be worn at all times. Also refer to GWP/CC/G6 & G7 ( working with machinary )
2. Falling in to the canal / river. Towpath asessments are to becarried out to heighlight |  |  |  |  | WE
the max width and weight that can be taken along the towpath.
These limits are not to be exceeded with out a reassessment from the Waterway Engineer.
3. BW safety footwear to be worn at all time during the works |  |  |  |  | WE
Staff
Future Measures to be Considered For Evaluation (to be completed during or after the task / activity)
Conclusion - Task Ok to Proceed
Risk is minimal , OK to proceed
Reference No | Assessment Date | Issue No. |  | Review Date
GWP/SM/G11 | 2001-09-04 | 1 |  | On Going
Assessed By: |  | Authorised By:
Darren Bramhall

## BW - AW 12
Region |  | Canal / Waterway
Sawley Marina |  | Grand Union Canal ( North )
Planned Operation
General Works Programme
Planned Task / Activity
Renewal of canal coping stones
Exposed Groups / Individual
BW staff
Hazardous Event & Potential Causes |  |  | Likelihood | Severity | Risk
1. Slips , trips , falls while setting up the site and removing and |  |  | Likely | 3 day event | medium
installing the new coping stones. |  |  |  | Minor injury
2. Falling into the canal, falling from the decks of the work boat
becoming trapped between the boat and the canal wall. |  |  | Likely | Minor injury | Medium
3. Loose the load of the stone copings |  |  | Likely | 3 day even | Low
minor injury
Control Measures |  |  |  |  | Action
1. Towpath is to have all obstacles removed, vegitation is to be removed from on top of the |  |  |  |  | Staff
canal copings, BW safety footwear is to be worn, working area is to be kept clean and tidy.
2. Boat deckings are to be clean and tidy , they are to have anti slip paint on deck sides. |  |  |  |  | WS
Stabilizing legs are to be in place to reduce movement of craft, mooring ropes are to be tied |  |  |  |  | Staff
correctly. Fenders are to be placed over the side of the boat to leave clear space between
the side of the boat and the canal wall.
3. Certified plant operator to be used, appropriate lifting equipment to be used. The load is to be |  |  |  |  | WE
kept as low to the ground as possible at all times. Consult GWP/CC/G5 Lifting Operations |  |  |  |  | WS
regular maintance of the craft to be undertaken in accordance with LOLER 1998
Future Measures to be Considered For Evaluation (to be completed during or after the task / activity)
Conclusion - Task Ok to Proceed
Compliance with LOLER regs 1998 will reduce the risk, OK to proceed
Reference No | Assessment Date | Issue No. |  | Review Date
GWP/SM/G12 | 2001-09-05 | 1 |  | Ongoing
Assessed By: |  | Authorised By:
Darren Bramhall

## BW - AW 13
Region |  | Canal / Waterway
Sawley Marina |  | Grand Union Canal ( North )
Planned Operation
General Works Programme
Planned Task / Activity
Grass Cutting ( Small Mechanical Cutter )
Exposed Groups / Individual
BW staff
Hazardous Event & Potential Causes |  |  | Likelihood | Severity | Risk
1. Carrying out preworks checks and plant maintance. There is the |  |  | Unlikely | Lost time to | medium
potential from the moving parts of the machinary and explosion from |  |  |  | major injury
the spillage of petrol on the exhaust.
2. Operation the cutter along side opf the canals and rivers, this |  |  | Likely | Lost time to | Medium
giving the rise to falling into the water. |  |  |  | fatality
Also refer to GWP/CC/G2 & G3
Control Measures |  |  |  |  | Action
1. Dead man switch is to be on at all times during cleaning of the blades and if applicable |  |  |  |  | Ws
keys are to be removed from the ignition. Staff operating machinary are to be experienced.
When refuelling the machinary only approved dispensing apparatus are to be used and any
spillage is to be cleaned up and dry before starting up the machinary.
2. The operator to be experienced and it to maintain concerntraction at all times. Machinary |  |  |  |  | WS
is to be situated in the centre of the towpath during cutting. The machinary is not to exceed
4 mph
Future Measures to be Considered For Evaluation (to be completed during or after the task / activity)
Conclusion - Task Ok to Proceed
Risk acceptable - Task ok to proceed.
Reference No | Assessment Date | Issue No. |  | Review Date
GWp/SM/G13 | 2002-01-09 | 1 |  | On going
Assessed By: |  | Authorised By:
Darren Bramhall

## BW - AW 14
Region |  | Canal / Waterway
Sawley Marina |  | Grand Union Canal ( North )
Planned Operation
General Works Programme
Planned Task / Activity
Operation of Locks
Exposed Groups / Individual
BW Staff & general public
Hazardous Event & Potential Causes |  |  | Likelihood | Severity | Risk
1. Operating of the lock gates and ground paddles giving the potential |  |  | Unlikely | First Aid to | Medium
for falling into the lock chamber / being struck by the balance beam |  |  |  | fatality
and the trapping of fingers / damage to limbs due to deffective
mechanisums.
2. Alighting and boarding of the craft to enter and exit the lock, |  |  | Unlikely | minor injury | Medium
causing the falling into the navigation. Also refer toGWP/CC/G4 |  |  |  | to fatality
Operation of Craft
3. Slips / trips & falls |  |  | Unlikely | Minor Injury | Medium
4. Exposure to inclemant weather and temperatures |  |  | Likely | Fatality | Medium
Control Measures |  |  |  |  | Action
1. Only experienced persons are to operate the locks, training is to be given to new persons |  |  |  |  | Ws
and where applicable a video demonstration should be shown if the inexperienced persons are |  |  |  |  | Hirer
hireing craft from any authorised oulet. Regular maintance to be carried out on the lock
mechanics to ensure they are in full working order.
2. Provision of appropriate safety clothing and footwear. Buoyancy aids, Throw Lines |  |  |  |  | Ws
and Thermal Blankets available on the craft. All craft have non-slip decking and |  |  |  |  | hirer
gunnells. Supervision of housekeeping.
3. All lock areas are to be free from obstacles, no storage of un authorised materials. Poor |  |  |  |  | Staff
surfacing is to be reported and repaired immediatley
4. Bw personnel are to be issued with the appropriate PPE, wet weather jackets and overalls |  |  |  |  | WS
gloves and boots / wellingtons.
Future Measures to be Considered For Evaluation (to be completed during or after the task / activity)
Video to be updated for the perpose of tuition for new visitors to the waterway
Conclusion - Task Ok to Proceed
Risk acceptable - Task ok to proceed.
Reference No | Assessment Date | Issue No. |  | Review Date
GWp/SM/G14 | 2002-01-30 | 2 |  | On going
Assessed By: |  | Authorised By:
Darren Bramhall

## BW - AW 15
Region |  | Canal / Waterway
Sawley Marina |  | Grand Union Canal ( North )
Planned Operation
General Works Programme
Planned Task / Activity
Driving BW vehicles ( 1 )
Exposed Groups / Individual
BW staff
Hazardous Event & Potential Causes |  |  | Likelihood | Severity | Risk
1. Carrying out the maintance checks and servicing of the lorry inc |  |  | Unlikely | First aid to | Low
the tipper, potential for trapping of fingers / being crushed by the cab |  |  |  | Fatality
as well as skin irritation from chemical used in maintance.
2. Collision with other vehicles / pedestrians / structures due to |  |  | Unlikely | First aid to | Medium
loss of vehicle control, incompetence, access to site via |  |  |  | fatality
narrow roads with poor visibility, poor weather conditions.
Control Measures |  |  |  |  | Action
1. Engine isolation switch to be in place and all hydraulic valves to be in the locked position |  |  |  |  | WS
cabs are to be propped incase the hydraulic values fail. Barrier creams and rubber gloves are
to be made available to prevent skin irritation.
2. Staff awareness of risks. All BW staff have experience of the routes used to the sites. |  |  |  |  | WS
Journey planning for all routes. Use of hands free phones. Staff to assess specific risks |  |  |  |  | T / Leader
before work commences. Consider the need to sign the site entrance, limit speed once off
public roads to 5 m.p.h. Consider need for a banksman to lead in delivery vehicles etc.
If access is from an embanked area, Bank to be assessed for stability by a competant
engineer. Consider need for fencing for demarkation of bank edge
Future Measures to be Considered For Evaluation (to be completed during or after the task / activity)
Conclusion - Task Ok to Proceed
Risk acceptable - Task ok to proceed.
Reference No | Assessment Date | Issue No. |  | Review Date
GWP/SM/G15 | 2002-01-09 | 1 |  | On Going
Assessed By: |  | Authorised By:
Darren Bramhall

## BW - AW 16
Region |  | Canal / Waterway
Sawley Marina |  | Grand Union Canal ( North )
Planned Operation
General Works Programme
Planned Task / Activity
Driving BW vehicles ( 2 )
Exposed Groups / Individual
BW Staff
Hazardous Event & Potential Causes |  |  | Likelihood | Severity | Risk
3. Setting up the lorry on site to allow lifting of materials, resulting in |  |  | Likely | Lost time to | Medium
the overturning of the lorry due to ground failure and or mechanical |  |  |  | fatality
failure and impactwith members of the general public
Control Measures |  |  |  |  | Action
3. The driver of the vehicle is to be experienced and hold a current driving license. He is to |  |  |  |  | Ws
hold a vaild hydraulic certificate for the operation of the ATLAS arm. The operator is to ensure
that the outriggers are fully extended at all times before starting the lifting and that the
spreader mats are placed underneath each leg. It is advised that the general day to day lifting
operations are covered by the operational lift plan.
Only trained and competent staff used for this operation. Regular recorded inspections
are carried out on all lifting gear and machinery. Banksman to assist with lifting operation
and to keep the general public away from the slewing area. Staff to carry out a visual
inspection of lifting equipment before use. Refer to BW safety policy for lifting operations
Appointed person to carry out all lift planning as per LOLER 1998 regs, BS 7121 part 1
BS 7121 part 3
Future Measures to be Considered For Evaluation (to be completed during or after the task / activity)
Conclusion - Task Ok to Proceed
Risk considered acceptable if BW Guidance is adhered to. Task ok to proceed
Reference No | Assessment Date | Issue No. |  | Review Date
GWP/SM/G16 | 2002-01-09 | 1 |  | On Going
Assessed By: |  | Authorised By:
Darren Bramhall

## BW - AW 17
Region |  | Canal / Waterway
Sawley Marina |  | Grand Union Canal ( North )
Planned Operation
General Works Programme
Planned Task / Activity
Navigation During Flooding Conditions
Exposed Groups / Individual
BW Staff / Other Boat owners
Hazardous Event & Potential Causes |  |  | Likelihood | Severity | Risk
1. Entering a river from the canal / navigating in a river that has high |  |  | Unlikely | Loss time | High
water levels / approaching a lock landing to allow entry in to a lock / |  |  |  | Injury to
Access and egress of the boat at anytime during the operating |  |  |  | Fatality
of the boat.
2. Operating any flood defence structure , flood gates / sluices |  |  | Unlikely | First Aid to | Medium
causing additional flooding and increasing water flows in certain |  |  |  | major injury
locations.
Control Measures |  |  |  |  | Action
1. British waterways has a designated flood team who ensure that when the river has deemed
to be in flood after contact by the EA, that the relevant flood gates ar put on. This is to prevent |  |  |  |  | Boat
access in to the river by ALL craft. Strong Stream warning signs are placed at locations |  |  |  |  | Operator
through out the navigation and have a 3 stage , this allows navigators to see that the river
levels are rising. Only experienced persons should take charge of a motor vessel at any time |  |  |  |  | BW Staff
and all passengers are to be wearing life vests and throw line are to be on board as well.
Adequate footwear is to be worn to prevent slipping of the gunnels in to the river.
If operators are unsure about the conditions in the river they should contact the local waterway
office who will inform them as to the current state of the river
Boat should have sufficient HP to assist navigation if in the river during flooding conditions
2. ONLY official waterway personnel should operate any flood structures.
Future Measures to be Considered For Evaluation (to be completed during or after the task / activity)
Ensure that all STRONG STREAM signs are installed and are visible
Conclusion - Task Ok to Proceed
River should only be entered for emergeny reasons and or if operators require to come of the river
task OK to proceed
Reference No | Assessment Date | Issue No. |  | Review Date
GWP/SM/G17 | 1 | 2002-01-09 |  | On Going
Assessed By: |  | Authorised By:
Darren Bramhall

## BW - GW 01
Region |  | Canal / Waterway
Sawley Marina |  | Grand Union Canal ( North )
Planned Operation
General Works Programme
Planned Task / Activity
Recovery of Debris, Rubbish and Obstructions
Exposed Groups / Individual
BW Staff / General Public
Hazardous Event & Potential Causes |  |  | Likelihood | Severity | Risk
1. Recovery of drums & containers causing chemical attack, |  |  | Unlikely | First Aid to | Medium
fumes and pollution |  |  |  | Major Injury
2. Litter picking and general clearance of rubbish causing exposure to |  |  | Likely | First Aid | Low
hazardous articles and contact with needles and syringes
3. Recovery of animal carcasses causing exposure to bacterial |  |  | Likely | Major Injury | High
Infections
4. Manuel handling, any large articles to be lifted with a second person |  |  | Unlikely | Minor Injury | Low
and or by mechanical assistance
Control Measures |  |  |  |  | Action
1. Staff vigilance for presence of hazardous items. Contact Fire Brigade for advice on type of |  |  |  |  | MW
Chemical identified. Chemical resistant gloves and overalls provided. If necessary, contain |  |  |  |  | Staff
area until assessment by competent person or agency, as detailed in BW Guidance for the
Handling and Disposal of Drums. Contact Waterway Supervisor for instructions.
2. Provision of Personal Protective Equipment. Follow BW Needles and Syringes Policy |  |  |  |  | MW
for the collection and disposal of such items. Staff video training. |  |  |  |  | Staff
3. Follow BW Safety Procedure - Disposal of Animal Carcasses. Staff awareness of |  |  |  |  | Staff
correct procedures and policy. |  |  |  |  | MW
4. Follow BW Manuel handling Procedure S10.3.12 |  |  |  |  | Staff
Future Measures to be Considered For Evaluation (to be completed during or after the task / activity)
Conclusion - Task Ok to Proceed
Risk considered acceptable if BW Guidance is adhered to. Task ok to proceed
Reference No | Assessment Date | Issue No. |  | Review Date
GWP/CC/001 | 2002-02-01 | 2 |  | Ongoing
Assessed By: |  | Authorised By:
Darren Bramhall

## BW - GW 02
Region |  | Canal / Waterway
Sawley Marina |  | Grand Union Canal ( North )
Planned Operation
General Works Programme
Planned Task / Activity
Installation and Replacement of Corporate Signage
Exposed Groups / Individual
BW Staff
Hazardous Event & Potential Causes |  |  | Likelihood | Severity | Risk
1. Poor manual handling caused by the lifting and moving of |  |  | Unlikely | Three Day | Medium
existing / new signage for Installation / Disposal. |  |  |  | Accident
2. Penatration of buired service cables during excavation for the |  |  | Unlikely | Fatality | High
installation / disposal of signage causing electricution / burns or
explosion.
3. Mixing / laying and transportation of concrete causing poor |  |  | Unlikely | Three Day | Medium
manual handling / exposure to hazardous materials |  |  |  | Accident
Control Measures |  |  |  |  | Action
1. Staff awareness and Video training. Individual assessment of manual handling |  |  |  |  | Staff
in accordance with BW Safety procedures. Limit manual handling to 25kg
where possible.
2. 'Cat test' carried out where considered appropriate. All excavations will be carefully |  |  |  |  | MW
hand dug. Local Utility Services contacted if required. |  |  |  |  | Staff
3. Control measures as item (1) for manual handling. Follow guidence in COSHH |  |  |  |  | MW
assessments for Cement and Natural Aggregates for concrete. Consider positioning |  |  |  |  | Staff
of process. Use of appropriate PPE.
Future Measures to be Considered For Evaluation (to be completed during or after the task / activity)
Conclusion - Task Ok to Proceed
Risk considered acceptable - Task ok to proceed.
Reference No | Assessment Date | Issue No. |  | Review Date
GWP/CC/002 | 2001-09-04 | 1 |  | Ongoing
Assessed By: |  | Authorised By:
Darren Bramhall

## BW - GW 03
Region |  | Canal / Waterway
Sawley Marina |  | Grand Union Canal ( North )
Planned Operation
General Works Programme
Planned Task / Activity
Maintenance to Long Term / Visitor Moorings
Exposed Groups / Individual
BW Staff / General Public
Hazardous Event & Potential Causes |  |  | Likelihood | Severity | Risk
1. General painting causing contact with hazardous materials and |  |  | Likely | First Aid | low
spillage causing pollution. Exposure to dust and debris during
preparation works.
2. Grass cutting and strimming causing exposure to hazards |  |  | See specified Risk Assessment
identified in risk assessment G6 and G7. Working on or adjacent
to water, Risk Assessment G2 and G3
3. Jet Washing causing exposure to high pressure water jet. |  |  | Unlikely | Lost Time | Low
See separate Method Statement and Risk Assessment
Control Measures |  |  |  |  | Action
1. Use Personal Protective Equipment. Follow COSHH procedures for all materials used. |  |  |  |  | Staff
Keep area well ventilated.
2. See specified Risk Assessment |  |  |  |  | Staff
3. See separate Method Statement and Risk Assessment for the 'Pressure Washing' |  |  |  |  | WS
risk assessment 008 |  |  |  |  | Staff
Future Measures to be Considered For Evaluation (to be completed during or after the task / activity)
Conclusion - Task Ok to Proceed
Risk considered acceptable - Task ok to proceed
Reference No | Assessment Date | Issue No. |  | Review Date
GWP/CC/003 | 2002-01-30 | 2 |  | Ongoing
Assessed By: |  | Authorised By:
Darren Bramhall

## BW - GW 04
Region |  | Canal / Waterway
Sawley Marina |  | Grand Union Canal ( North )
Planned Operation
General Works Programme
Planned Task / Activity
Electrical / Mechanical Works
Exposed Groups / Individual
BW Staff / Public
Hazardous Event & Potential Causes |  |  | Likelihood | Severity | Risk
1. Contact electrical equipment incl. Mains AC, rectified DC, |  |  | Unlikely | Fatality | High
batteries, capacitors and standby generators, including autostart.
causing electricution, burns and fires.
2. Contact with mechanical equipment incl. Potential energy |  |  | Unlikely | Major Injury | Medium
(mass and height), moving machinery and stored energy (springs)
3. Contact with chemicals causing fire, exothermic reactions, |  |  | Unlikely | Major | Medium
corrosive effects.
Control Measures |  |  |  |  | Action
For all of the above hazards.
Only 'Authorised Persons' will undertake M&E work. Staff concerned will only work within |  |  |  |  | WS
limits of knowledge, skill and experience. All information will be supplied to the staff along |  |  |  |  | PE (M&E)
with instructions on type of work and equipment to be repaired / maintaned. All energy |  |  |  |  | Staff
sources which cause a potential risk will be identified and isolated before work commences.
All energy sources will be quarantined by the use of locks / barriers etc.
Work will only commence when it is certain that uncontrolled energy releases cannot take
place. Staff to contact the Project Engineer for any advice required before work commences.
Future Measures to be Considered For Evaluation (to be completed during or after the task / activity)
Conclusion - Task Ok to Proceed
Once preventative and protective measures in place then risk considered acceptable. Task ok to proceed.
Reference No | Assessment Date | Issue No. |  | Review Date
GWP/CC/004 | 2001-09-04 | 1 |  | Ongoing
Assessed By: |  | Authorised By:
Darren Bramhall

## BW - GW 05
Region |  | Canal / Waterway
Sawley Marina |  | Grand Union Canal ( North )
Planned Operation
General Works Programme
Planned Task / Activity
Routine Lock Maintenance (1)
Exposed Groups / Individual
BW Staff
Hazardous Event & Potential Causes |  |  | Likelihood | Severity | Risk
1. General cleaning of lock sites causing exposure to cleaning |  |  | Likely | Lost Time | Medium
materials and slippery surfaces
2. Glass replacement causing exposure to glass splinters / cuts |  |  | Unlikely | First Aid | Low
3. Drain clearance causing exposure to micro-biological hazards |  |  | Unlikely | Three Day | Medium
4. General Plumbing works using a Blow lamp causing burns / fires |  |  | Unlikely | Major Injury | Medium
Control Measures |  |  |  |  | Action
1. Wear appropriate PPE for cleaning works. Follow COSHH Assessments / manufacturers |  |  |  |  | Staff
guidance for all cleaning materials. Erect signs to warn public of slippery floors.
2. Wear appropriate PPE. Risks considered acceptable |  |  |  |  | Staff
3. Risk considered low. Preventative and protective measures used such as Leptospirosis |  |  |  |  | WS
cards, barrier creams, good hygiene and personal protective clothing to minimise risk |  |  |  |  | Staff
4. Only competent and trained staff used for plumbing works. Use appropriate PPE. |  |  |  |  | WS
Fire extinguishers available at lock sites. |  |  |  |  | Staff
Future Measures to be Considered For Evaluation (to be completed during or after the task / activity)
Conclusion - Task Ok to Proceed
Once protective and preventative measures in place, task ok to proceed.
Reference No | Assessment Date | Issue No. |  | Review Date
GWP/CC/005 | 2001-09-04 | 1 |  | Ongoing
Assessed By: |  | Authorised By:
Darren Bramhall

## BW - GW 06
Region |  | Canal / Waterway
Sawley Marina |  | Grand Union Canal ( North )
Planned Operation
General Works Programme
Planned Task / Activity
Routine Lock Maintenance (2)
Exposed Groups / Individual
BW Staff / General Public
Hazardous Event & Potential Causes |  |  | Likelihood | Severity | Risk
1. General painting causing contact with hazardous materials and |  |  | Likely | First Aid | low
spillage causing pollution. Exposure to dust and debris during
preparation works.
2. Grass cutting and strimming causing exposure to hazards |  |  | See specified Risk Assessment
identified in G6 and G7
3. Jet Washing causing exposure to high pressure water jet. |  |  | Unlikely | Lost Time | Low
See separate Method Statement and Risk Assessment
Control Measures |  |  |  |  | Action
1. Use Personal Protective Equipment. Follow COSHH procedures for all materials used. |  |  |  |  | Staff
Keep area well ventilated.
2. See specified Risk Assessment |  |  |  |  | Staff
3. See separate Method Statement and Risk Assessment for the 'Pressure Washing' |  |  |  |  | WS
Staff
Future Measures to be Considered For Evaluation (to be completed during or after the task / activity)
Conclusion - Task Ok to Proceed
Risk considered acceptable - Task ok to proceed
Reference No | Assessment Date | Issue No. |  | Review Date
GWP/CC/006 | 2001-09-04 | 1 |  | Ongoing
Assessed By: |  | Authorised By:
Darren Bramhall

## BW - GW 07
Region |  | Canal / Waterway
Sawley Marina |  | Grand Union Canal ( North )
Planned Operation
General Works Programme
Planned Task / Activity
Sanitary Station Cleaning
Exposed Groups / Individual
BW Staff / General Public
Hazardous Event & Potential Causes |  |  | Likelihood | Severity | Risk
1. Slips, trips or falls caused by slippery surfaces or obstructions |  |  | Likely | Three Day | Medium
during the cleaning works. |  |  |  | Accident
2. Contact with cleaning agents causing burns, eye injury, |  |  | Unlikely | Three Day | Low
respiratory illnesses or skin irritation |  |  |  | Accident
and contact with human feaces
Control Measures |  |  |  |  | Action
1. Safety footwear worn by BW staff during the cleaning works. Erect 'Cleaning in Progress' |  |  |  |  | Staff
and 'Wet Floor' signs before the work commences to warn the general public.
2. Staff to wear gloves and overalls during the cleaning works. Follow manufacturers |  |  |  |  | WS
guidance and COSHH Assessments when using cleaning agents. |  |  |  |  | Staff
Waterway Supervisor to ensure that COSHH Assessment received for any Cleaning
Agents before usage.
3. Hands and faces are to be to be washed to remove any smell or possible contamination |  |  |  |  | WS
Staff
Future Measures to be Considered For Evaluation (to be completed during or after the task / activity)
Conclusion - Task Ok to Proceed
Task ok to proceed.
Reference No | Assessment Date | Issue No. |  | Review Date
GWP/CC/007 | 2002-01-30 | 2 |  | Ongoing
Assessed By: |  | Authorised By:
Darren Bramhall

## BW - GW 08
Region |  | Canal / Waterway
Sawley Marina |  | Grand Union Canal ( North )
Planned Operation
General Works Programme
Planned Task / Activity
Working with Pressure Washers
Exposed Groups / Individual
BW Staff
Hazardous Event & Potential Causes |  |  | Likelihood | Severity | Risk
1. Contact with water jet caused by operator error or slips, trips or |  |  | Unlikely | Three Day | Medium
falls. |  |  |  | Accident
2. Environmental pollution of surrounding area and the navigation |  |  | Unlikely | - | -
resulting in damage to wildlife and prosecution
Control Measures |  |  |  |  | Action
1. Only trained and experienced operator to use pressure washer. Where possible have |  |  |  |  | MW
at least two people at the worksite. Particular care taken when working from either a |  |  |  |  | Staff
workboat / platform or tower. Consider the use of a body harness and safety line where a
danger of a fall / slip exists e.g working at weirs. Waterway supervisor to advise staff on
levels of safety precautions. Follow control measures for slips, trips or falls.
2. Refuel machinery away from navigation to avoid spills. Regular machine inspections and |  |  |  |  | MW
maintenance. Contact Environment Agency immediately if pollution occurs. Follow |  |  |  |  | Staff
BW Environmental Code of Practice. Waterway Supervisor to implement best practice.
Future Measures to be Considered For Evaluation (to be completed during or after the task / activity)
Conclusion - Task Ok to Proceed
Risk considered acceptable. Task ok to proceed.
Reference No | Assessment Date | Issue No. |  | Review Date
GWP/CC/008 | 2001-09-04 | 1 |  | Ongoing
Assessed By: |  | Authorised By:
Darren Bramhall

## BW - GW 09
Region |  | Canal / Waterway
Sawley Marina |  | Grand Union Canal ( North )
Planned Operation
General Works Programme
Planned Task / Activity
Painting Works
Exposed Groups / Individual
BW Staff / General Public
Hazardous Event & Potential Causes |  |  | Likelihood | Severity | Risk
1. General painting causing contact with hazardous materials and |  |  | Likely | First Aid | low
spillage causing pollution. Exposure to dust and debris during
preparation works.
Control Measures |  |  |  |  | Action
1. Use Personal Protective Equipment. Follow COSHH procedures for all materials used. |  |  |  |  | WS
Keep area well ventilated. When painting next to Navigation, a 'Spill Kit' will be available on |  |  |  |  | Staff
site at all times. Paint pre-ordered along with the Hazard Identification sheets which are |  |  |  |  | WE
passed to the Planning Supervisor for the production of COSHH Assessments
Future Measures to be Considered For Evaluation (to be completed during or after the task / activity)
Conclusion - Task Ok to Proceed
Risk considered acceptable - Task ok to proceed
Reference No | Assessment Date | Issue No. |  | Review Date
GWP/CC/010 | 2001-09-04 | 1 |  | Ongoing
Assessed By: |  | Authorised By:
Darren Bramhall

## BW - GW 10
Region |  | Canal / Waterway
Sawley Marina |  | Grand Union Canal ( North )
Planned Operation
General Works Programme
Planned Task / Activity
Excavation & Filling Operations
Exposed Groups / Individual
BW Staff / General Public
Hazardous Event & Potential Causes |  |  | Likelihood | Severity | Risk
1. Working adjacent to a 180 / 360 Degree Excavator, or Hiab |  |  | Unlikely | Fatality | High
with exposure to collision, entrapment and crushing
2. Working on or adjacent to excavated surfaces / open trenches |  |  | Unlikely | Major Injury | Medium
causing slips, trips or falls. Falling objects from excavator or
banksman into working area.
3. Working with compaction equipment with exposure to the |  |  | Likely | Minor Injury | Medium
risks outlined in GWP/CC/G6 and GWP/CC/G7
Control Measures |  |  |  |  | Action
1. Only trained and experienced staff to operate machinery. Staff awareness of risks |  |  |  |  | Staff
associated with working adjacent to machinery. PPE worn at all times including Hard Hat,
Safety Footwear, Gloves.
2. Excavated area / working area to be kept clean and tidy. PPE worn at all times as above. |  |  |  |  | Staff
3. See See control measures for GWP/CC/G6 and GWP/CC/G7 |  |  |  |  | Staff
Future Measures to be Considered For Evaluation (to be completed during or after the task / activity)
Conclusion - Task Ok to Proceed
Risk considered acceptable - Task ok to proceed.
Reference No | Assessment Date | Issue No. |  | Review Date
GWP/CC/010 | 2001-09-04 | 1 |  | Ongoing
Assessed By: |  | Authorised By:
Darren Bramhall

## BW - GW 11
Region |  | Canal / Waterway
Sawley Marina |  | Grand Union Canal ( North )
Planned Operation
General Works Programme
Planned Task / Activity
Installation of Fencing / Bollards
Exposed Groups / Individual
BW Staff
Hazardous Event & Potential Causes |  |  | Likelihood | Severity | Risk
1. Poor manual handling caused by the lifting and moving of |  |  | Unlikely | Three Day | Medium
existing / new fencing or bollards for Installation / Disposal. |  |  |  | Accident
2. Penatration of buired service cables during excavation for the |  |  | Unlikely | Fatality | High
installation / disposal of fencing or bollards causing electricution /
burns or explosion.
3. Mixing / laying and transportation of concrete causing poor |  |  | Unlikely | Three Day | Medium
manual handling / exposure to hazardous materials |  |  |  | Accident
Control Measures |  |  |  |  | Action
1. Staff awareness and Video training. Individual assessment of manual handling |  |  |  |  | Staff
in accordance with BW Safety procedures. Limit manual handling to 25kg
where possible.
2. 'Cat test' carried out where considered appropriate. All excavations will be carefully |  |  |  |  | MW
hand dug. Local Utility Services contacted if required. |  |  |  |  | Staff
3. Control measures as item (1) for manual handling. Follow guidence in COSHH |  |  |  |  | MW
assessments for Cement and Natural Aggregates for concrete. Consider positioning |  |  |  |  | Staff
of process. Use of appropriate PPE.
Future Measures to be Considered For Evaluation (to be completed during or after the task / activity)
Conclusion - Task Ok to Proceed
Risk considered acceptable - Task ok to proceed.
Reference No | Assessment Date | Issue No. |  | Review Date
GWP/CC/011 | 2001-09-04 | 1 |  | Ongoing
Assessed By: |  | Authorised By:
Darren Bramhall

## BW - GW 12
Region |  | Canal / Waterway
Sawley Marina |  | Grand Union Canal ( North )
Planned Operation
General Works Programme
Planned Task / Activity
Piling Works
Exposed Groups / Individual
BW Staff / General Public
Hazardous Event & Potential Causes |  |  | Likelihood | Severity | Risk
1. Loss of pile control during handling (mechanical / manual) caused |  |  | Unlikely | Major Injury | Medium
by high winds, twisting action during clutching, inadequate lifting
equipment.
2. Pile driving causing exposure to excessive noise, flying debris |  |  | Likely | Major Injury | High
and the risks outlined in GWP/CC/G6 and GWP/CC/G7
- 'Working with Machinery'
Control Measures |  |  |  |  | Action
1. Implement all control measures outlined in GWP/CC/G5 - 'Lifting Operations'. PPE to |  |  |  |  | Staff
include safety footwear, gauntlets, hard hat for the handling and lifting of piles.
2. Exclusion zone around the piling operation to reduce risk to the general public. |  |  |  |  | Staff
PPE as above including Ear defenders. Also see control measures for GWP/CC/G6 & G7
3. Only certified plant operators are to be used. A lift plan is to be implace for the loading of |  |  |  |  | WE
materials before the commencement of the works, LOLER 1998 regs are applicable |  |  |  |  | WS
Future Measures to be Considered For Evaluation (to be completed during or after the task / activity)
Conclusion - Task Ok to Proceed
Risk considered acceptable - Task ok to proceed
Reference No | Assessment Date | Issue No. |  | Review Date
GWP/CC/012 | 2001-09-04 | 1 |  | Ongoing
Assessed By: |  | Authorised By:
Darren Bramhall

## BW - GW 13
Region |  | Canal / Waterway
Sawley Marina |  | Grand Union Canal ( North )
Planned Operation
General Works Programme
Planned Task / Activity
Feeder Maintenance
Exposed Groups / Individual
BW Staff
Hazardous Event & Potential Causes |  |  | Likelihood | Severity | Risk
1. Poor manual handling caused by the lifting and moving of |  |  | Unlikely | Three Day | Medium
vetetation or obstructions from the feeder channel, filling of voids. |  |  |  | Accident
2. Slips trips or falls caused by working on an uneven / slippery |  |  | Likely | Minor | Medium
surface in running water
3. Mixing / laying and transportation of concrete causing poor |  |  | Unlikely | Three Day | Medium
manual handling / exposure to hazardous materials |  |  |  | Accident
Control Measures |  |  |  |  | Action
1. Staff awareness and Video training. Individual assessment of manual handling |  |  |  |  | Staff
in accordance with BW Safety procedures. Limit manual handling to 25kg
where possible.
2. Work in pairs when in feeder channel. Wear safety boots at all times during the works
3. Control measures as item (1) for manual handling. Follow guidence in COSHH
assessments for Cement and Natural Aggregates for concrete. Consider positioning
of process. Use of appropriate PPE.
Future Measures to be Considered For Evaluation (to be completed during or after the task / activity)
Conclusion - Task Ok to Proceed
Risk considered acceptable - Task ok to proceed.
Reference No | Assessment Date | Issue No. |  | Review Date
GWP/CC/013 | 2001-09-04 | 1 |  | Ongoing
Assessed By: |  | Authorised By:
Darren Bramhall

## BW - GW 14
Region |  | Canal / Waterway
Sawley Marina |  | Grand Union Canal ( North )
Planned Operation
General Works Programme
Planned Task / Activity
Water Control / Operation of Back Pumps /Manual sluices
Exposed Groups / Individual
BW Staff
Hazardous Event & Potential Causes |  |  | Likelihood | Severity | Risk
1. Poor manual handling caused by the operation of the sluice |  |  | Unlikely | Three Day | Medium
mechanism |  |  |  | Accident
2. Crushing or entrapment in the sluice mechanism caused by |  |  | Unlikely | Major Injury | High
operator error or worn gearing
3. Electricution from operation of back pumps caused by poor |  |  | Unlikely | Fatal | High
maintenance of equipment.
4. Working Alone, especially when carrying out flooding dutys and at |  |  | Likely | Fatality | High
night
Control Measures |  |  |  |  | Action
1. Staff awareness and Video training. Individual assessment of manual handling |  |  |  |  | Staff
in accordance with BW Safety procedures. Ensure correct positioning for sluice
operation. Request assistace if required. Sluice to be kept well maintained.
2. Manditory inspection procedures ensure that sluice kept well maintained. Experienced |  |  |  |  | Staff
and competent staff used for this operation. Wear safety gloves and footwear to prevent
slipping
3. Annual M&E Inspections ensure equipment kept well maintained. Operate equipment |  |  |  |  | Staff
as per manufacturers operational procedures. Experienced and competent staff to
operate pumps.
4. Follow BW Guidance on Working Alone S10.3.3 |  |  |  |  | Staff
WS
Future Measures to be Considered For Evaluation (to be completed during or after the task / activity)
Conclusion - Task Ok to Proceed
Risk considered acceptable - Task ok to proceed.
Reference No | Assessment Date | Issue No. |  | Review Date
GWP/CC/014 | 2002-02-01 | 2 |  | Ongoing
Assessed By: |  | Authorised By:
Darren Bramhall

## BW - GW 15
Region |  | Canal / Waterway
Sawley Marina |  | Grand Union Canal ( North )
Planned Operation
General Works Programme
Planned Task / Activity
Cleaning Weirs and Culverts
Exposed Groups / Individual
BW Staff
Hazardous Event & Potential Causes |  |  | Likelihood | Severity | Risk
1. Poor manual handling caused by the lifting and moving of |  |  | Unlikely | Three Day | Medium
vetetation or obstructions from weirs or inlet / outlet of culverts. |  |  |  | Accident
2. Slips trips or falls caused by working on an uneven / slippery |  |  | Likely | Fatality | Medium
surface in running water also while working from
the canal bank
3. Debris and obstructions present inside culverts. Entry into a |  |  | Unlikely | Fatal | High
confined space.
Control Measures |  |  |  |  | Action
1. Staff awareness and Video training. Individual assessment of manual handling |  |  |  |  | Staff
in accordance with BW Safety procedures. Limit manual handling to 25kg
where possible.
2. Work in pairs when possible. Wear safety boots at all times during the works. |  |  |  |  | Staff
Possible need for the works to be carried out by two persons, especially on larger weirs
and lock bypass culverts. Harnesses may need to be worn during task
3. Staff will not enter a culvert under any circumstances. In these instances, Waterway |  |  |  |  | Staff
Supervisor to arrange for specialised and fully confined space trained staff / contractors to |  |  |  |  | WS
to carry out the works required.
If site has a closed in culvert then NO ENTRY is allowed until assessed by the engineers in
accordance with CONFINED SPACES S10.2.2
4. Entry in to culverts will be covered by the ' confined spaces' and is to be assessed by an |  |  |  |  | WE
appropriate trained person to level 1 /2
Future Measures to be Considered For Evaluation (to be completed during or after the task / activity)
Conclusion - Task Ok to Proceed
Risk considered acceptable - Task ok to proceed.
Reference No | Assessment Date | Issue No. |  | Review Date
GWP/CC/015 | 2002-02-01 | 2 |  | Ongoing
Assessed By: |  | Authorised By:
Darren Bramhall

## BW - GW 16
Region |  | Canal / Waterway
Sawley Marina |  | Grand Union Canal ( North )
Planned Operation
General Works Programme
Planned Task / Activity
Dredging
Exposed Groups / Individual
BW Staff / General Public
Hazardous Event & Potential Causes |  |  | Likelihood | Severity | Risk
1. BW staff / general public coming into contact with moving |  |  | Likely | Fatality | High
machinery.
2. BW staff / general public falling into deep mud |  |  | Likely | Fatality | High
3. Mechanical lifting with Crane Boat causing loss of load control |  |  | Unlikely | Major Injury | Medium
due to incorrect use of equipment, inadequate maintenance
4. BW staff suffering the effects of contamination from dredgings |  |  | Unlikely | 3 day injury | Low
Control Measures |  |  |  |  | Action
1. Trained and experienced operators only used for the operation operation of all plant and |  |  |  |  | WS/WF
craft on site.
1&2. The working area should be enclosed to prohibit public access and warning sign should |  |  |  |  | WS/WF
be erected to advise of the risks and dangers.
3. Only trained and competent staff used for this operation. Regular recorded inspections |  |  |  |  | WS
are carried out on all lifting gear and machinery. Banksman to assist with lifting operation |  |  |  |  | Staff
and to keep the general public away from the slewing area. Staff to carry out a visual
inspection of lifting equipment before use. Refer to BW safety policy for lifting operations
4. Inert river dredgings only. Protective clothing should be worn and hands cleaned before |  |  |  |  | Staff
consuming food and drink, prior to visiting the toilet and at the end of the day.
Future Measures to be Considered For Evaluation (to be completed during or after the task / activity)
Conclusion - Task Ok to Proceed
Risk considered acceptable if BW Guidance is adhered to. Task ok to proceed
Reference No | Assessment Date | Issue No. |  | Review Date
GWP/CC/016 | 2001-09-04 | 1
Assessed By: |  | Authorised By:
Darren Bramhall

## BW - GW 17
Region |  | Canal / Waterway
Sawley Marina |  | Grand Union Canal ( North )
Planned Operation
General Works Programme
Planned Task / Activity
Working on Canal / River weirs
Exposed Groups / Individual
BW staff
Hazardous Event & Potential Causes |  |  | Likelihood | Severity | Risk
1. Accessing the weirs by craft, alighting from the craft on to the weir |  |  | Likely | Faitality | High
crest. Exposure to slips / trips
2. Stanking of the weir to allow repairs, working on the weir crest. |  |  | Likely | Major injury | High
Fatality
3. Craneing loads down on to the weir crest, or from the crest back |  |  | Likely | Major injury | High
on the craft. |  |  |  | Fatality
4. Falling / Slipping in to the river. Exposure to waterborn diseases. |  |  | Likely | Fatality | High
Control Measures |  |  |  |  | Action
1. 2. 3. 4. The weirs are to only be accessed by craft when the rivers are not in flood, plant is to have
been regulally mainatained. All personnel that are working on the weirs are to have
life jackets on and are to be tethered to a nominated banksperson. Wellington boots are to be worn
Hard hats and rubber gloves. All surfaces that are to be accessed are to be cleaned of any
existing residual material. Only certified and experienced plant operators
are to be used on this type of work. Good house keeping is to be in place with adequate facilities
for the washing of hand before meal times.
Compliance with LOLER 1998 when carrying out any form of lifting. |  |  |  |  | WE
WS
Staff
Future Measures to be Considered For Evaluation (to be completed during or after the task / activity)
Conclusion - Task Ok to Proceed
Only experienced staff to carry out this type of works and they are to be planned outside of anticipated
flooding times. If so OK to proceed
Reference No | Assessment Date | Issue No. |  | Review Date
GWP/SM/017 | 2001-09-05 | 1 |  | Ongoing
Assessed By: |  | Authorised By:
Darren Bramhall

## BW - GW 18
Region |  | Canal / Waterway
Sawley Marina |  | Grand Union Canal ( North )
Planned Operation
General Works programme
Planned Task / Activity
Putting on of Flood gates at locations on the GUCN
Exposed Groups / Individual
BW Staff
Hazardous Event & Potential Causes |  |  | Likelihood | Severity | Risk
1. Falls, slips and trips as details in Risk Assessments G2 & G3 |  |  | Likely | First Aid / | High
working Adjacent to the Navigation |  |  |  | Major Injury
2. Gaining access to the o/s flood gate. This achieved typically by
the use of small cog boat, falaling in to the river while accessing and |  |  | Likely | fatality | High
egressing from the boat
3.Potential for Hypothermia due to inclemant weather, snow , wind |  |  | Unlikely | fatality | Medium
rain
Control Measures |  |  |  |  | Action
1. Considered high risk due to number of incidents. Use of Safety Footwear at all times. |  |  |  |  | WS
Staff to report in at end of shifts. Manditory inspection procedures identify repairs and minor |  |  |  |  | Staff
works required to rectify defects.
2. Life jackets to be worn at all times, experiened boat operator. Lock keeper to inform |  |  |  |  | Flood
flood co ordinator that he is carrying out works and again when task is completed. If possible |  |  |  |  | Co'tor
the task to be carried out by 2 persons
3. BW Staff are issued with PPE , in extreme climate conditions perhaps thermal clothing |  |  |  |  | WS
may be required to be worn.
Future Measures to be Considered For Evaluation (to be completed during or after the task / activity)
Look in to the potential of mechanising the flood gates
Conclusion - Task Ok to Proceed
Task OK to proceed
Reference No | Assessment Date | Issue No. |  | Review Date
GWP/SM/018 | 2002-02-01 | 1 |  | On going
Assessed By: |  | Authorised By:
Darren Bramhall

## WRG LANC 1
Region |  | Canal / Waterway |  |  |  | Not applicabe to WRG projects at Tewitfiled 2004
North West |  | Lancaster Canal - Northern Reaches
Planned Operation
Restoration of Tewitfield Locks
Planned Task / Activity
Removal of silt and debris by hand from the Lock Chambers at Tewitfied
Exposed Groups / Individual
Waterway Recovery Group volunteers
Hazardous Event & Potential Causes |  |  | Likelihood | Severity | Risk
1. Personal injury due to partially exposed debris in the lock chambers / surounding area. |  |  | Likely | First Aid / Major Injury | High
2. WRG Volunteers suffering the effects of contamination from dredgings. |  |  | Unlikely | 3 day injury | Low
Water Diversion
wetness etc. - slurry
drowning
Control Measures |  |  |  |  | Action
1. The working area within each lock chamber will be protected by a suitable safety fence above / around each chamber. |  |  |  |  | Site Leader / Volunteers
2. Suitable protective clothing should be worn and volunteers advised to wash hands before consuming food and drink, prior to visiting the toilet and at the end of the day. |  |  |  |  | Site Leader / Volunteers
3. Work area to be maintained in tidy manner and scrambling over infill to be minimised. |  |  |  |  | Site Leader / Volunteers
4. No volunteers will work above the lock on the plateau when volunteers are working in the chamber.
5. British Waterways are to collect and test samples of the silt for traces of noxious / harmful substances and provide appropriate Health and Safety advice to the WRG Site Leader. |  |  |  |  | BW / EA / Site Leader
Future Measures to be Considered For Evaluation (to be completed during or after the task / activity)
Conclusion - N/A
RISK NOT APPLICABLE TO CURRENT TEWITFIELD PROJECTS - NO WORK TO BE CONDUCTED IN LOCK CHAMBER
Reference No | Assessment Date | Issue No. |  | Review Date
WRG/LANC 01 | 2004-01-17 | 3 |  | Ongoing
Assessed By: |  | Authorised By:
Rick Barnes

## WRG LANC 2
Region |  | Canal / Waterway
North West |  | Lancaster Canal - Northern Reaches
Planned Operation
Restoration of Tewitfield Locks
Planned Task / Activity
Use of Hand Tools
Exposed Groups / Individual
Waterway Recovery Group volunteers
Hazardous Event & Potential Causes |  |  | Likelihood | Severity | Risk
1. Use of non-powered hand tools causing striking, cutting, ejection of material, dust inhalation, crushing and trapping due to poor equipment maintenance, operator error or poor housekeeping. |  |  | Unlikely | First Aid to Major Injury | Medium
Control Measures |  |  |  |  | Action
1. The use of hand tools by WRG volunteers is to be in accordance with the guidelines laid out in the Practical Restoration Handbook. |  |  |  |  | Site Leader / Volunteers
2. Personal Protective Equipment suitable to the specified task is to be worn and will be made available as required and where appropriate, equipment safety guards will be supplied. |  |  |  |  | Site Leader / Volunteers
3. Equipment is to be well maintained and inspected by user prior to use - any damaged equipment is to be put beyond use whilst awaiting repair and the work party leader informed. |  |  |  |  | Site Leader / Volunteers
4. All equipment will be stored in a safe and proper manner when not in use. |  |  |  |  | Site Leader / Volunteers
5. Persons involved in operations that may result in flying debris (eg chipping out) shall wear suitable eye protection. Suitable eye protection will be made available to each volunteer. |  |  |  |  | Site Leader / Volunteers
Future Measures to be Considered For Evaluation (to be completed during or after the task / activity)
Conclusion - Task to Proceed
Risk considered acceptable - task to proceed.
Reference No | Assessment Date | Issue No. |  | Review Date
WRG/LANC 02 | 2004-07-17 | 4 |  | Ongoing
Assessed By: |  | Authorised By:
Rick Barnes

## WRG LANC 3
Region |  | Canal / Waterway |  |  |  | Not applicabe to WRG projects at Tewitfiled 2004
North West |  | Lancaster Canal - Northern Reaches
Planned Operation
Restoration of Tewitfield Locks
Planned Task / Activity
Use of Ladders
Exposed Groups / Individual
Waterway Recovery Group volunteers
Hazardous Event & Potential Causes |  |  | Likelihood | Severity | Risk
1. Use of ladders for access to work area causing exposure to potential falls from heights and falling objects. Causes include working at heights, unsecured ladders, overbalancing, over reaching, uneven surface at foot of ladder, slipping on rung or a defective ladder. |  |  | Unlikely | Major Injury to Fatality | High
Control Measures |  |  |  |  | Action
1. All ladders to meet BS EN 131. All metal ladders will have slip resistant rubber or plastic feet. |  |  |  |  | Site Leader / Volunteers
2. All ladders will be regularly inspected. |  |  |  |  | ditto
3. Ladders to be tied securely and footed on a level surface |  |  |  |  | ditto
4. All ladders to be the correct length and set at the correct angle. |  |  |  |  | ditto
5. No ladder to be used in excess of 11m long and should extend at least 1.05m above the landing place. |  |  |  |  | ditto
6. Only commercial grade ladders used i.e.. Grade 2 or 3. |  |  |  |  | ditto
Future Measures to be Considered For Evaluation (to be completed during or after the task / activity)
RISK NOT ENVISAGED TO BE APPLICABLE TO CURRENT TEWITFIELD PROJECTS
Conclusion - Task to Proceed
Risk considered acceptable - task to proceed.
Reference No | Assessment Date | Issue No. |  | Review Date
WRG/LANC 03 | 2004-07-17 | 2 |  | Ongoing
Assessed By: |  | Authorised By:
Rick Barnes

## WRG LANC 4
Region |  | Canal / Waterway
North West |  | Lancaster Canal - Northern Reaches
Planned Operation
Restoration of Tewitfield Locks
Planned Task / Activity
Confined Spaces
Exposed Groups / Individual
Waterway Recovery Group volunteers
Hazardous Event & Potential Causes |  |  | Likelihood | Severity | Risk
1. Entry into a confined space with potential exposure to Gases, fumes or vapours, Oxygen deficiency and entrapment or disabling injury. |  |  | Unlikely | Fatality | High
Control Measures |  |  |  |  | Action
1. Follow the safety procedures for Confined Spaces as defined in the Practical Restoration Handbook. In addition, BW will be asked for advice regarding confined spaces and their assessment as per the BW policy. |  |  |  |  | Site Leader
2. If the Hazard Level is 1 or 2 then only suitably trained BW staff (or WRG volunteers suitably trained by BW or to a recognised standard) will undertake the task if it is necessary. |  |  |  |  | Site leader / Volunteers
3. WRG Volunteers will be made aware of the policies on confined spaces in the Practical Restoration Handbook and the BW Safety Policy as part of the site brief. |  |  |  |  | Site leader / Volunteers
4. WRG Volunteers will not work inside the paddle culverts or By-wash culverts without prior survey by an approved engineer, satisfactory completion of the additional associated paperwork and use of suitable protective equipment. In this instance no work will be conducted inside culverted channels |  |  |  |  | BW / Site leader / Volunteers
5. Volunteers are not to work alone. |  |  |  |  | Site leader / Volunteers
Future Measures to be Considered For Evaluation (to be completed during or after the task / activity)
Conclusion - Task to Proceed
Task to proceed. No work is to be conducted in the culverted sections of by-wash channels at Tewitfield. The Practical restoration handbook and the BW Safety Policy on Confined Spaces must be adhered to.
Reference No | Assessment Date | Issue No. |  | Review Date
WRG/LANC 04 | 2004-07-26 | 5 |  | Ongoing
Assessed By: |  | Authorised By:
Rick Barnes

## WRG LANC 5
Region |  | Canal / Waterway
North West |  | Lancaster Canal - Northern Reaches
Planned Operation
Restoration of Tewitfield Locks
Planned Task / Activity
Sharp Drops
Exposed Groups / Individual
Waterway Recovery Group volunteers
Hazardous Event & Potential Causes |  |  | Likelihood | Severity | Risk
1. Restoration of locks includes working in and around abandoned and drained / partially drained locks causing exposure to potential falls from heights and falling objects. Causes include people working adjacent to the sides of the lock, beyond safety barriers and fences and above other volunteers working in the lock. |  |  | Unlikely | Major Injury to Fatality | High
Control Measures |  |  |  |  | Action
1. WRG volunteers will be instructed during the site safety brief to work in accordance with the guidelines and practices defined in the Practical Restoration Handbook, and not to work adjacent to the edges of the locks. |  |  |  |  | Site Leader / Volunteers
2. At each of the locks 5, 6 and 7, safety barriers will be erected by a scaffolding contractor to a specification / design that meets British Waterways' standards. This work will be completed prior to the volunteers arriving on site. No changes to the scaffolding structures will be made by volunteers. |  |  |  |  | BW / Site Leader / Volunteers
3. No work shall be conducted on top of the lock sides if it requires crossing a safety fence. Volunteers will be instructed as part of the site brief not to cross the line of or move safety fences. Failure to comply with this instruction will result in the individual(s) being suitably disciplined and may result in their removal from site. |  |  |  |  | Site Leader / Volunteers
4. Volunteers will not enter the area of dense vegetation next to the fourth lock from bottom unless they are wearing suitable fall arrest equipment which is attached to a suitable anchor point. Any activity around this lock will be limited to the areas surrounding the top pan of the by-wash and the outflow at the tail of the lock to rectify / finish any work from last year. |  |  |  |  | Site Leader / Volunteers
Future Measures to be Considered For Evaluation (to be completed during or after the task / activity)
Conclusion - Task to Proceed
Risk considered acceptable - task to proceed.
Reference No | Assessment Date | Issue No. |  | Review Date
WRG/LANC 05 | 2004-07-26 | 4 |  | Ongoing
Assessed By: |  | Authorised By:
Rick Barnes

## WRG LANC 6
Region |  | Canal / Waterway
North West |  | Lancaster Canal - Northern Reaches
Planned Operation
Restoration of Tewitfield Locks | [5 empty] | Not applicabe to WRG projects at Tewitfiled 2004
Planned Task / Activity
Use / Spraying of Herbicidal Weed Killers
Exposed Groups / Individual
Waterway Recovery Group volunteers
Hazardous Event & Potential Causes |  |  | Likelihood | Severity | Risk
1. Restoration of locks includes working in and around structures that become overgrown with brush and other scrub. To minimise nugatory effort, areas within a structure that have been cleared of brush are to be sprayed with a herbicidal weedkiller to prevent / minimise re-growth, facilitating subsequent removal of infill. It is possible that the person spraying the ground may become directly contaminated with the herbicide. |  |  | Unlikely | Major Injury to Fatality | High
2. Indirect contamination of volunteers through subsequent handling of sprayed material / infill. |  |  | Unlikely | 3 day injury | Medium
Control Measures |  |  |  |  | Action
1. The volunteer spraying the herbicide shall work in a methodical manner such that it is not necessary to walk through / across an area that have just been sprayed, or to work below an area that has just been sprayed. |  |  |  |  | Site Leader / Volunteers
2. The volunteer spraying the herbicide shall not spray above waist height. |  |  |  |  | Volunteer
3. The volunteer spraying the herbicide shall wear suitable protective clothing in accordance with the manufacturers instructions. |  |  |  |  | Volunteer
4. Spraying will not be conducted in windy conditions and when spraying there must be a minimium of additional volunteers present. Additional care must be taken not to contaminate the public right of way. |  |  |  |  | Volunteer
5. Volunteers working subsequently on a sprayed area are to wear suitable protetive clothing and are to wash before eating, going to the toilet and at the end of each working day. |  |  |  |  | Site Leader / Volunteers
Future Measures to be Considered For Evaluation (to be completed during or after the task / activity)
Conclusion - Task to Proceed
HERBICIDES SHOULD NOT BE USED ON THIS SITE DUE TO LOCALITY OF FARM LAND AND ADJOINING WATERCOURSE
Reference No | Assessment Date | Issue No. |  | Review Date
WRG/LANC 06 | 2004-07-17 | 2 |  | Ongoing
Assessed By: |  | Authorised By:
Rick Barnes

## WRG LANC 7
Region |  | Canal / Waterway
North West |  | Lancaster Canal - Northern Reaches
Planned Operation
Restoration of Tewitfield Locks
Planned Task / Activity
Removal of silt and debris from derelict By-wash
Exposed Groups / Individual
Waterway Recovery Group volunteers
Hazardous Event & Potential Causes |  |  | Likelihood | Severity | Risk
1. Personal injury / trip hazard due to partially exposed debris in the chamber. |  |  | Likely | First Aid / Major Injury | High
2. WRG Volunteers suffering the effects of contamination from dredgings |  |  | Unlikely | 3 day injury | Low
Control Measures |  |  |  |  | Action
1. The working area will be localised round each By-wash. The working area for locks 5, 6 and 7 will be on the off-side of the canal away from the tow path, which will remain open to the public. |  |  |  |  | BW / Site Leader / Volunteers
2. Suitable protective clothing should be worn whilst working and hands cleaned before consuming food and drink, prior to visiting the toilet and at the end of the day. |  |  |  |  | Site Leader / Volunteers
3. Work area to be maintained in tidy order and passage over unexcavated sections and removed infill is to be minimised. |  |  |  |  | Site Leader / Volunteers
4. British Waterways are to collect and test samples of the silt for traces of noxious / harmful substances and provide appropriate Health and Safety advice to the WRG Site Leader. |  |  |  |  | BW / EA / Site Leader
Future Measures to be Considered For Evaluation (to be completed during or after the task / activity)
Conclusion - Task to Proceed
Risk considered acceptable. Task to proceed
Reference No | Assessment Date | Issue No. |  | Review Date
WRG/LANC 07 | 2004-07-26 | 3 |  | Ongoing
Assessed By: |  | Authorised By:
Rick Barnes

## WRG LANC 8
Region |  | Canal / Waterway
North West |  | Lancaster Canal - Northern Reaches
Planned Operation
Restoration of Tewitfield Locks
Planned Task / Activity
Operation of Plant and Vehicles On or close to site
Exposed Groups / Individual
WRG Volunteers / BW staff / General Public
Hazardous Event & Potential Causes |  |  | Likelihood | Severity | Risk
1. Collision with other vehicles / pedestrians / structures due to loss of vehicle control, incompetence, access to site via narrow roads with poor visibility, poor weather conditions. |  |  | Unlikely | Lost time to Fatality | High
2. Vehicles reversing causing collision with other vehicles, pedestrians or structures |  |  | Unlikely | Lost time to Fatality | High
3. Unsafe vehicle due to poor maintenance causing the above |  |  | Unlikely | Lost time to Fatality | High
4. Injury to volunteers due to crushing |  |  | Unlikely | Lost time to Fatality | High
5. Injury to the public resulting from inappropriate operation and mud from tyres |  |  | Unlikely | Lost time to Fatality | High
Control Measures |  |  |  |  | Action
1. Volunteers awareness of risks. All WRG drivers will have been assessed for suitabilty as an operator and shall be able to show Driver Authorisation cards on request. Once off public roads speed will be limited to 10 m.p.h. The driver shall consider the need for a banksman to lead in vehicles (including deliveries and on site operations). |  |  |  |  | Site leader / WRG Authorised Operators
2. The driver will appoint a suitable person to act as banksman to assist with reversing. Audible warning on some vehicles. All banksmen must wear a hi-vis vest / jacket. |  |  |  |  | Site leader / WRG Authorised Operators
3. Staff carry out daily vehicle checks. All vehicles will have had suitable servicing and comply with legal requirements (MOT etc.) where applicable. |  |  |  |  | Site leader / WRG Authorised Operators
4. Volunteers to be made aware of the plant to be operated and the hazards during the safety brief at the start of the camp. Volunteers are required to sign that they understand the brief prior to working on site. Authorised drivers to be aware of surroundings and appoint a suitable banksman as required. |  |  |  |  | Site leader / Authorised Operators / Volunteers
5. No wheeled personell carrying vehicles will be used on the towpath during the project. Motorised wheelbarrows, wheelbarrows and personnel may operate along the towpath periodically to transport materials and equipment to the work site. |  |  |  |  | Site leader / Authorised Operators / Volunteers
6. Drivers of plant are to be aware of the ground conditions before attempting to drive across it and should inspect the route to be taken for ground conditions, overhanging trees, ditches and manholes etc. Plant should be driven directly up a slope (not across it) and re-assessment will be required if conditions change and the ground becomes wet. |  |  |  |  | Authorised Operators
7. Access over the fields will be along the edges of the fields unless otherwise advised by the land owner. The farmer has agreed to the operation of plant through the farm and will advise his staff. Drivers will be advised to be aware of the staff and livestock. Speed across fields and through the farm will be kept to a minimum. |  |  |  |  | Authorised Operators
8. Reversing will be kept to a practical minimum. All turning operations must be conducted only after the driver is satisfied that no pedestrian hazard exists. |  |  |  |  | Authorised Operators
Future Measures to be Considered For Evaluation (to be completed during or after the task / activity)
Driver Authorisation scheme assessment is a pre-requisite for all drivers.
Conclusion - Task to Proceed
Risk considered acceptable. Task to proceed
Reference No | Assessment Date | Issue No. |  | Review Date
WRG/LANC 08 | 2004-07-26 | 4 |  | Ongoing
Assessed By: |  | Authorised By:
Rick Barnes

## WRG LANC 9
Region |  | Canal / Waterway
North West |  | Lancaster Canal - Northern Reaches
Planned Operation
Restoration of Tewitfield Locks
Planned Task / Activity
Working with machinery / plant on site (including cement mixers, brush cutters and low power generators)
Exposed Groups / Individual
Waterway Recovery Group volunteers
Hazardous Event & Potential Causes |  |  | Likelihood | Severity | Risk
1. Exposure to fumes, vapours including exhaust fumes causing asphyxiation, respiratory disease, eye injuries or fire / explosion. |  |  | Likely | 3 day injury | Medium
2. Exposure to excessive noise >85dba causing hearing impairment and exposure to vibration causing HAVS or muscular skeletal injuries. |  |  | Unlikely | 3 day injury | Medium
3. Contact with moving parts caused by operator error / unguarded machinery or slips, trips or falls. |  |  | Unlikely | Major Injury | Medium
4. Electrocution due to poor equipment maintenance, Incorrect power supply, water ingress and operator error. |  |  | Unlikely | Fatal | High
Control Measures |  |  |  |  | Action
1. The working area should be localised round each By-wash. The working area will be on the off-side of the canal away from the tow path, which will remain open to the public. In the case of Lock 5, plant will be situated sufficiently far away from the green land to minimise any hazard to passing pedestrians. |  |  |  |  | BW / Site Leader / Volunteers
2. Suitable protective clothing should be worn and hands cleaned before consuming food and drink, prior to visiting the toilet and at the end of the day. |  |  |  |  | Site Leader / Volunteers
3. Work area to be maintained in tidy order and passage over unexcavated sections and removed infill is to be minimised. |  |  |  |  | Site Leader / Volunteers
4. Fuels to be stored in suitable, clearly marked containers in a location away from naked flame and sunlight. |  |  |  |  | Site Leader / Volunteers
Future Measures to be Considered For Evaluation (to be completed during or after the task / activity)
Conclusion - Task to Proceed
Risk considered acceptable. Task to proceed
Reference No | Assessment Date | Issue No. |  | Review Date
WRG/LANC 09 | 2004-07-26 | 3 |  | Ongoing
Assessed By: |  | Authorised By:
Rick Barnes

## WRG LANC 10
Region |  | Canal / Waterway
North West |  | Lancaster Canal - Northern Reaches
Planned Operation
Restoration of Tewitfield Locks
Planned Task / Activity
Mixing and using Mortar and Cement
Exposed Groups / Individual
Waterway Recovery Group volunteers
Hazardous Event & Potential Causes |  |  | Likelihood | Severity | Risk
1. Exposure to cement powder resulting in respiratory difficulties skin burnes and eye injuries. |  |  | Likely | 3 day injury | Medium
2. Contact with mixed mortar or cement resulting in eye or skin injuries. |  |  | Likely | 3 day injury | Medium
3. Contact with moving parts of a cement mixer (where used) caused by operator error or slips, trips or falls. |  |  | Unlikely | Major Injury | Medium
Control Measures |  |  |  |  | Action
1. Mixing Cement / Mortar will be conducted a convenient distance from the bulk of the work group and away from public rights of way. PPE to the required standard will be provided and should be worn by all personnel handling cement powder and mixed product including gloves, goggles and respiratory mask. All exposed skin should be covered. |  |  |  |  | BW / Site Leader / Volunteers
2. Suitable protective clothing should be worn whilst working (including gloves, dust masks and goggles) and hands cleaned before consuming food and drink, prior to visiting the toilet and at the end of the day. Volunteers will be briefed during the site safety talk about the hazards of using Lime. |  |  |  |  | Site Leader / Volunteers
3. The cement mixer will be convenintly sited on suitably flat even ground and located sufficiently remotely from the work group to minimise noise and material hazards. The area is to be kept tidy and free of trip hazards. Volunteers will not reach into the cement mixer or insert hand tools whilst the drum is turning. All machine parts (except drum) will be guarded or enclosed. |  |  |  |  | Site Leader / Volunteers
Future Measures to be Considered For Evaluation (to be completed during or after the task / activity)
Conclusion - Task to Proceed
Risk considered acceptable. Task to proceed
Reference No | Assessment Date | Issue No. |  | Review Date
WRG/LANC 10 | 2004-07-26 | 3 |  | Ongoing
Assessed By: |  | Authorised By:
Rick Barnes

## WRG LANC 11
Region |  | Canal / Waterway
North West |  | Lancaster Canal - Northern Reaches
Planned Operation
Restoration of Tewitfield Locks
Planned Task / Activity
Manual Handling
Exposed Groups / Individual
Waterway Recovery Group volunteers
Hazardous Event & Potential Causes |  |  | Likelihood | Severity | Risk
1. Risk of injury due to manual handling and lifting objects and hand excavation |  |  | Likely | 3 Day injury | Meduim
2. Risk of Injury due to manual handling on rough / uneven / slippery ground and surfaces. |  |  | Likely | 3 Day injury | Meduim
Control Measures |  |  |  |  | Action
1. Work is to be conducted in accordance with the guidance contained in the Practical Restoration Handbook (Chapter 3, Paragraph 8 - Health & Safety Section 2, Manual Lifting and Handling). The PRH will be available on site. |  |  |  |  | Site Leader / Volunteers
2. Access routes to the work sites will be cleared of vegetation and made as even as practicable. This will be the first task for each area of the site on which we are working. For areas requiring access down steep banks, temporary steps will be cut into the bank and hazardous debris moved or removed. Where necessary, temporary orange hazard barrier fencing will be installed. |  |  |  |  | Site Leader / Volunteers
3. Safety footwear is highly recommended and worn by many volunteers. It is made clear to volunteers that without such footwear they will be unable to conduct certain tasks such as lifting etc. Where tasks dictate, such as lifting or the use of cutting machinery, suitable safety footwear will be made available to volunteers. Such tasks on the Tewitfield flight will include scrub clearance using slashers and lifting of heavy stones such as those located in the mouth of the by-wash adjacent to lock 5. |  |  |  |  | Site Leader / Volunteers
Future Measures to be Considered For Evaluation (to be completed during or after the task / activity)
Conclusion - Task to Proceed
Risk considered acceptable. Task to proceed
Reference No | Assessment Date | Issue No. |  | Review Date
WRG/LANC 11 | 2004-07-26 | 3 |  | Ongoing
Assessed By: |  | Authorised By:
Rick Barnes

## WRG LANC 12
Region |  | Canal / Waterway
North West |  | Lancaster Canal - Northern Reaches
Planned Operation
Restoration of Tewitfield Locks
Planned Task / Activity
Working adjacent to a watercourse and farm land (illness)
Exposed Groups / Individual
Waterway Recovery Group volunteers
Hazardous Event & Potential Causes |  |  | Likelihood | Severity | Risk
1. Risk of Injury due to farm animals and machinery. |  |  | Unlikely | Fatal | High
2. Risk of illness contracted from organisms and bacteria carried in the watercourse, animals or animal faeces. |  |  | Unlikely | Fatal | High
Control Measures |  |  |  |  | Action
1. For any works to lock 1, volunteers will be delivered to site via a mini-bus / van so reducing the need for pedestrian access through the farmyard. For locks 4, 5, 6 and 7 volunteers will be delivered by mini-bus to either the top or bottom of the flight and instructed to walk up / down the towpath and cross the approproiate pedestrian bridges or the accommodation bridge at the tail of lock 5 . As part of the safety brief, volunteers will be instructed to stay away from the animals, be wary of moving machinery and ensure that the operator of the machines has seen them before approaching. Similarly, the farmer has granted permission for access via the farm and understands that there may be vehicles and pedestrians present. |  |  |  |  | Site Leader / Volunteers
2. As part of the Safety brief at the start of the camp, volunteers will be informed of the hazards associated with biological organisms and the importance of good hygiene. Water, anti-bacterial soap and towels will be available at the site and should be used prior to going to the toilet, eating and drinking etc. Lunch breaks will be taken away from the locks, either at the top or bottom of the flight utilising the existing washing and toilet facilities or the BW mobile mess unit (if desired). |  |  |  |  | Site Leader / Volunteers
Future Measures to be Considered For Evaluation (to be completed during or after the task / activity)
Conclusion - Task to Proceed
Risk considered acceptable. Task to proceed
Reference No | Assessment Date | Issue No. |  | Review Date
WRG/LANC 12 | 2004-07-26 | 3 |  | Ongoing
Assessed By: |  | Authorised By:
Rick Barnes